## Slide 1
Client Referral | COI Referral | Event Planning
Process Checklist |  | 
PREPARE |  | 
ROLE | STEP | DETAILS/TIPS
Client Service Associate | Validate Event with Stakeholders Due: 10 Weeks Before Event | Validate Event with Advisor Confirm the event focus and topics with the Advisor to ensure it’s clear what the objective and intent of the event is Be sure to take notes for reference later throughout the planning process Brainstorm potential sponsors and speakers for the event Determine a target date, location, and time that the event would take place When setting the target date be sure to take into consideration the amount of time that is required to plan an event of this complexity Create an event budget and set goals (i.e., number of attendees, revenue needed to cover costs, etc.)
 |  | Validate Event Resources Validate the target event date with the rest of the team to ensure there are no scheduling conflicts (i.e., holidays, vacations, meetings, etc.) Investigate venues that meet the event requirements and create a short list This could be done via a combination of web research and calls the venues, but the primary objective is to create a prioritized list of venue options that meet the event requirements, including capacity and availability on target date Contact the identified sponsors and speakers to confirm interest in participating and attending the event Identify sources for collateral and content for the event (i.e., presentation content, invitations, etc.)
Marketing
Webinar Planning | Social Media Content
Description: This workflow describes all the steps required to plan, prepare, and conduct an event. Events can come in many different forms depending on the firm’s objectives. Some examples of typical Advisor events include but are not limited to client appreciation dinners, topical seminars, networking events, prospecting events, etc. Generally most firms, depending on the available resources, aim to plan and host 2-4 events each year.
© 2015 SEI. This information is proprietary. No further distribution is intended.

## Slide 2
Process Checklist |  | 
PREPARE |  | 
ROLE | STEP | DETAILS/TIPS
Client Service Associate | Confirm Resources & Stakeholders Due: 8 Weeks Before Event | Evaluate Options & Confirm a Venue Request for proposals from the potential venues on the identified on the short list Review the proposals and conduct onsite visits to the venues This provides an opportunity to ask more in-depth questions in person and also to confirm the venue ‘s appearance is as expected Identify the best venue option for the firm's event based on the proposal and findings from the onsite visit Negotiate rates, sign contracts, and pay deposits to confirm the venue Be sure to file those documents internally for record-keeping purposes
 |  | Confirm Event with Stakeholders Notify the team of the finalized date and location of the event Finalize the sponsors and speakers and ensure they understand their roles and responsibilities leading up to the event If necessary, execute formal contracts reinforcing those responsibilities Identify the creators of content for the presentation Describe what type of content is needed so the creators can get started working on their portion of the presentation
Client Service Associate | Coordinate Guest Invitations Due: 6 Weeks Before Event | Organize & Send Save The Dates Identify the guest list based on the event requirements and confirm with the team This is particularly important since client relationships are so sensitive, so be sure to confirm that the appropriate people are on the guest list Validate the contact information for the guest list to ensure it’s up-to-date Draft and send out the save-the-date cards to the guest list recipients Best practice is to mail out hard copies of the cards for formality, though email can be used if delivery time and costs are both issues Provide copies of the cards to the team for reference, in case anyone contacts them asking for details about the event
 |  | Draft & Distribute Invitations Draft the event invitation and gain compliance approval from your broker-dealer as necessary Be sure to proofread any content and double check any information that might’ve been used within the invite for accuracy Finalize the invitations, after reviewing proofs, and send out the invitations to the guests Best practice is to mail an extra copy to yourself along with the others, so the firm can ensure the mail gets delivered and also has a sense of how long it will take to get delivered Provide copies of the invites to the team for reference, in case anyone contacts them asking for details about the event
Marketing
Client Referral | COI Referral | Event Planning
Webinar Planning | Social Media Content
© 2015 SEI. This information is proprietary. No further distribution is intended.

## Slide 3
Process Checklist |  | 
PREPARE |  | 
ROLE | STEP | DETAILS/TIPS
Client Service Associate | Coordinate Marketing for Events Due: 4 Weeks Before Event | Perform Promotional Activities Create advertisements for the event as appropriate, if the event is public knowledge Examples of typical ways to promote an event: Add the event date and location onto the firm’s website Post ads for the event in nearby locations or newspapers Add the event to any local business event calendars Invite organizations of interest and COIs (i.e., Chambers of Commerce, neighborhood associations, etc.) to the event Send out a RSVP reminder to the guest list to ensure they respond Consider using a report for tracking RSVPs as they come in and consider sharing it with other team members who might receive RSVPs as well “RSVP Tracking Report” Template (right-click underlined text to open hyperlink to template)
 |  | Plan Marketing Content for Event Determine the type of handouts that will be needed for the event (i.e., brochures, forms, surveys, etc.) Identify the sources of all the content that will be needed for the event These sources could be both people drafting and creating the content as well as vendors printing and providing the content Set deadlines for creators of content and ensure everyone is aware of their respective due dates
Client Service Associate | Finalize Resources for Event Due: 1 Week Before Event | Finalize Attendance & Notify Stakeholders Track RSVPs via a tracking document and contact all non-respondents This can be performed either via a phone call or email depending on the event type and preferences of the firm Confirm the final guest head count based on the RSVPs that have been received Notify the event caterer of the final head count, if applicable This might require filling in the final head count on a contract, signing it, and sending it to the caterer Provide the final guest list to the team for reference
 |  | Collect & Prepare Event Collateral Print name tags for all guests, including the team members if appropriate Be sure to double check the spelling of all names Collect and organize all event content from all sources Print and prepare all the signage, handouts, and marketing for the event
Marketing
Client Referral | COI Referral | Event Planning
Webinar Planning | Social Media Content
© 2015 SEI. This information is proprietary. No further distribution is intended.

## Slide 4
Marketing
Process Checklist |  | 
CONDUCT |  | 
ROLE | TASK | DETAILS/TIPS
Client Service Associate | Conduct Event | Prepare Room & Manage Guests Prepare the room 1-3 hours before the start of event in order to: Set-up and test the projector and any other technology Distribute presentation copies and marketing materials Set-up name tags and the general welcome area Make sure the room, catering, and signage are all in order Greet and guide guests throughout the event as necessary Have a firm calendar ready to make appointments between guests and team members as necessary Manage any event handouts or forms that need to be distributed and collected at specific times throughout the event Generally it’s best practice to distribute and collect an evaluation form at the end of the presentation in order to collect feedback from the attendees
Process Checklist |  | 
PREPARE |  | 
ROLE | STEP | DETAILS/TIPS
Client Service Associate | Finalize Event Presentation Due: 5 Days Before Event | Conduct Presentation Review & Training Collect all presentation content from sources on appropriate deadlines Review and revise the presentation as needed Gain compliance approval of the presentation from your broker-dealer as necessary Conduct a rehearsal with the speakers to practice roles, content, and transitions from one speaker to another Finalize the presentation and distribute it to all the speakers for reference Load the presentation to appropriate computers or storage drives
Client Service Associate | Confirm Final Event Details Due: 3 Days Before Event | Contact & Confirm Guests Contact all the guests to confirm their attendance at the event Reconfirm the event details (i.e., time, location, directions, parking, etc.) If necessary, offer to send any attendees directions to the venue
 |  | Contact & Confirm Venue Contact the venue to confirm the event details (i.e., timing, attendees, catering, AV, room, etc.)
Client Referral | COI Referral | Event Planning
Webinar Planning | Social Media Content
© 2015 SEI. This information is proprietary. No further distribution is intended.

## Slide 5
Marketing
Client Referral | COI Referral | Event Planning
Webinar Planning | Social Media Content
© 2015 SEI. This information is proprietary. No further distribution is intended.
Process Checklist |  | 
FOLLOW-UP |  | 
ROLE | TASK | DETAILS/TIPS
Client Service Associate | Manage Event Follow-Up Tasks Due: 1 Week After Event | Execute any time-sensitive items (i.e., sign contracts, pay bills, etc.) Create and update any contact records in the CRM for reporting purposes It’s important to update all contacts who attended the event or received any event communications, so the team always has a point of reference as to when the last point of contact was with the contact Schedule any meetings as follow-up to the event This includes meetings between attendees and team members as well as any internal team meetings within the firm Follow-up with any no-show attendees as appropriate Considering sending them a summary and copy of the materials from the event or inviting them to the next event
Client Service Associate | Debrief with Team After Event Due: 2 Weeks After Event | Meet internally with the team to discuss the event Review progress to event goals and objectives identified at the start of the event planning process Celebrate any accomplishments but also identify opportunities for improvement of the next event of this kind Identify pros and cons of the event, as a post-mortem exercise for the team Collect feedback from the team and identify any changes that should be noted for the next event Record notes from the debrief for reference when planning the next event