## Slide 1
Client Referral | COI Referral | Event Planning
Process Checklist |  | 
PREPARE |  | 
ROLE | STEP | DETAILS/TIPS
Client Service Associate | Validate Webinar with Stakeholders Due: 6 Weeks Before Webinar | Validate Webinar with Advisor Confirm the webinar focus and topics with the Advisor to ensure it’s clear what the objective and intent of the webinar is Be sure to take notes for reference later throughout the planning process Identify potential moderators and speakers for the webinar Determine a target date, location, and time the webinar would take place When setting the target date be sure to take into consideration the amount of time that is required to plan a webinar of this complexity Determine the budget and technical requirements (i.e., attendee capacity, ability to record webinar, etc.) for hosting the webinar
 |  | Validate Webinar Resources Validate the target webinar date with the rest of the team to ensure there are no scheduling conflicts (i.e., holidays, vacations, meetings, etc.) Investigate and choose a webinar software that meets the webinar requirements Typically firms will choose one webinar software and continue to use it overtime so that: The experience is consistent and familiar for both the firm and the attendees each webinar The firm can get a price break from the webinar vendor for purchasing a more long-term plan Contact and confirm the moderators and speakers for the webinar Generally you need the speakers to take on three primary roles during the webinar: Introductions Moderator Main speaker Identify sources for presentation content for the webinar Begin building out the basic outline and framework for the presentation to help with this process
Marketing
Webinar Planning | Social Media Content
Description: This workflow describes all the steps required to plan, prepare, and conduct a webinar. Webinars can cover many different topics depending on the firm’s objectives. Some examples of typical Advisor webinar topics include but are not limited to economic updates, benefits of investing / having a financial advisor, or different planning topics (i.e., tax, estate, retirement, etc.). Webinars provide a great opportunity for connecting with many contacts simultaneously in a cost and time efficient manner.
© 2015 SEI. This information is proprietary. No further distribution is intended.

## Slide 2
Process Checklist |  | 
PREPARE |  | 
ROLE | STEP | DETAILS/TIPS
Client Service Associate | Determine Webinar Specifics Due: 4 Weeks Before Webinar | Identify Structure & Requirements Determine how presenters will interact with the audience when it comes to the following: PowerPoint slides Chat functionality within webinar software Polling / surveying Q & A sessions Identify the audio, video, and technical requirements for the webinar Determine whether the firm will require technical assistance from the vendor on the day of the webinar Develop a marketing and communications plan, which includes deadlines for deliverables leading up to the webinar Determine what the webinar follow-up will be (i.e., automated survey, multiple emails, sales call, etc.) Generally most webinar follow-ups include the following: An evaluation survey for feedback A thank you for attending message Some call-to-action Materials from the webinar A recording of the webinar
 |  | Identify & Confirm Guest List Identify the guest list based on the webinar requirements and confirm with the team Validate the contact information for the guest list to ensure it’s up-to-date Determine & Coordinate Content Determine the agenda and topics for the presentation Identify the creators of content for the presentation Describe what type of content is needed so the creators can get started working on their portion of the presentation Set deadlines for creators of content and ensure everyone is aware of their respective due dates
Marketing
© 2015 SEI. This information is proprietary. No further distribution is intended.
Client Referral | COI Referral | Event Planning
Webinar Planning | Social Media Content

## Slide 3
Process Checklist |  | 
PREPARE |  | 
ROLE | STEP | DETAILS/TIPS
Client Service Associate | Coordinate Attendee Invitations Due: 3 Weeks Before Webinar | Develop & Test Registration Page Develop a landing page for registration for the webinar for the attendees It’s recommended that the registration be under a unique URL for marketing and reporting purposes Complete development of the landing page and test the registration process end-to-end to ensure it works
 |  | Send Invitation & Schedule Reminders Draft the content for the invitations and reminder emails leading up to the webinar Gain compliance approval from your broker-dealer as necessary Be sure to proofread any content and double check any information that might’ve been used within the invite for accuracy Finalize and send out the initial email invitation to the webinar Best practice is to send a test communication to yourself before sending it to all the contacts to ensure the message went through as expected and that the technology works Provide copies of the invites to the team for reference, in case anyone contacts them asking for details about the webinar Schedule reminder emails to be sent out leading up to webinar, as appropriate
Client Service Associate | Finalize Webinar Presentation Due: 1 Week Before Webinar | Conduct Presentation Review & Training Collect all presentation content from sources on appropriate deadlines Review and revise the presentation as needed Gain compliance approval from your broker-dealer as necessary Conduct a rehearsal with the speakers to practice roles, content, and transitions from one speaker to another Finalize the presentation and distribute it to the speakers for reference Load the presentation to the appropriate computers or storage drives
Client Service Associate | Confirm Final Webinar Details Due: 3 Days Before Webinar | Remind Attendees & Speakers Send a reminder to all attendees with the webinar details (e.g. time, dial-in, etc.) Send instructions to the speakers to log-in to the webinar 15 minutes early
Marketing
Client Referral | COI Referral | Event Planning
Webinar Planning | Social Media Content
© 2015 SEI. This information is proprietary. No further distribution is intended.

## Slide 4
Marketing
Process Checklist |  | 
CONDUCT |  | 
ROLE | TASK | DETAILS/TIPS
Client Service Associate | Conduct Webinar | Prepare Webinar & Manage Attendees Prepare and test all technology being used during the webinar 30-45 minutes before to ensure it’s working properly Test all audio and mute all attendees 15-30 minutes before the webinar Greet guests as they log on and guide speakers throughout the presentation Be prepared to address any technology or audio issues that might arise during the session
© 2015 SEI. This information is proprietary. No further distribution is intended.
Client Referral | COI Referral | Event Planning
Webinar Planning | Social Media Content
Process Checklist |  | 
FOLLOW-UP |  | 
ROLE | TASK | DETAILS/TIPS
Client Service Associate | Manage Webinar Follow-Up Tasks Due: 1 Week After Webinar | Send thank you notes to the attendees for attending and to the speakers for their time preparing and presenting This can be done via email as an initial follow-up to the webinar Distribute the webinar replay video as appropriate Typically a firm would distribute the replay video via email to the webinar attendees and also post it on the firm’s website Review all polls and questions for potential follow-up opportunities See if the is an opportunity to create a marketing piece (i.e., blog post, newsletter, etc.) using the information that was gathered during the webinar Review the webinar internally and collect feedback from the team as a debrief exercise Record notes from the debrief for reference when planning the next webinar